## ClickUp Tasks
Task Name | Assignee | Day / Due | Priority | Status | List | Description
Install stellar-cli + Rust + wasm target; deploy hello-world contract to testnet; verify on stellar.expert | P1 | Day 1 | Urgent | to do | Day 1 - Foundations | THE critical de-risk task. If toolchain fights you, find out now not Day 5.
Set up Next.js repo, GitHub, branching; connect Stellar JS SDK to testnet; fund test keypair via Friendbot | P2 | Day 1 | High | to do | Day 1 - Foundations | Confirm a balance read works end of day.
Scaffold Next.js + Tailwind; build 3 empty role-view shells (OFW/Family/Store) + role switcher | P3 | Day 1 | High | to do | Day 1 - Foundations | Fake data only, no logic.
Create Supabase project; draft schema (profiles, inventory, wishlist, settlements); set up ClickUp board; write pitch paragraph | P4 | Day 1 | High | to do | Day 1 - Foundations | Schema draft, RLS comes Day 2.
GATE: hello-world contract live on testnet AND frontend reads a balance | All | Day 1 | Urgent | to do | Day 1 - Foundations | Do not advance to Day 2 until green.
Write deposit_and_split contract fn (i128, fixed-point stroops, #![no_std]); unit test with stellar-cli | P1 | Day 2 | Urgent | to do | Day 2 - Core Contract | Stores 3 sub-balances in contract storage.
Build POST /api/deposit calling contract; code-review P1 Rust for overflow + access control | P2 | Day 2 | High | to do | Day 2 - Core Contract | Use checked arithmetic. Backup contract dev.
OFW view: allocation sliders (sum to 100%), Send button -> API -> show sub-balances | P3 | Day 2 | High | to do | Day 2 - Core Contract
Finalize Supabase schema, enable RLS, seed inventory + demo users (OFW/Family/Store) | P4 | Day 2 | High | to do | Day 2 - Core Contract
GATE: OFW moves sliders, sends, sees 3 real on-chain sub-balances | All | Day 2 | High | to do | Day 2 - Core Contract
Add lock_escrow + release_escrow to same contract; test happy path locally | P1 | Day 3 | Urgent | to do | Day 3 - Escrow + Inventory | Lock holds grocery funds; release sends to merchant.
API routes /api/escrow/lock + /api/escrow/release; wire responses; error handling in this layer | P2 | Day 3 | High | to do | Day 3 - Escrow + Inventory
Family view: browse inventory, build wishlist, Request approval. Store view: see order, Mark delivered | P3 | Day 3 | High | to do | Day 3 - Escrow + Inventory
Wishlist + settlement tables on Supabase realtime; Store view live-updates; start pitch deck outline | P4 | Day 3 | Normal | to do | Day 3 - Escrow + Inventory
GATE: escrow lock works on-chain; wishlist creates a real locked escrow | All | Day 3 | High | to do | Day 3 - Escrow + Inventory
Wire release_escrow to Family Confirm Delivery path; test lock->confirm->funds at store; verify on stellar.expert | P1 | Day 4 | Urgent | to do | Day 4 - Close The Loop | MAKE OR BREAK DAY.
Connect full chain deposit->split->lock->release through API routes, reflected in UI | P2 | Day 4 | Urgent | to do | Day 4 - Close The Loop
Confirm Delivery button -> release -> success; Store shows Paid; receipt card UI (tx hash + items) | P3 | Day 4 | High | to do | Day 4 - Close The Loop
On release: decrement Supabase inventory + mark settlement; realtime updates Store; pitch deck draft | P4 | Day 4 | High | to do | Day 4 - Close The Loop
GATE: FULL GOLDEN PATH end to end works on one click-through. TAG THIS COMMIT. | All | Day 4 | Urgent | to do | Day 4 - Close The Loop | This is your safety net.
Contract edge cases (re-deposit, double-confirm, zero balance) no panic; write demo script | P1 | Day 5 | High | to do | Day 5 - Harden + Polish | SCOPE FREEZE at start of day.
Friendly error states everywhere (no stack traces); loading spinners on every chain call | P2 | Day 5 | High | to do | Day 5 - Harden + Polish
Lola Test polish: hide jargon, big buttons, GCash styling, success animations, Tagalog key labels | P3 | Day 5 | High | to do | Day 5 - Harden + Polish
Demo data reset script (one command to clean state); pitch deck near-final; rehearse with P1 | P4 | Day 5 | High | to do | Day 5 - Harden + Polish
Full dress rehearsal x3, timed; P1 drives; lock demo script; record backup video of perfect run | All | Day 6 | Urgent | to do | Day 6 - Demo Readiness
Deploy stable final contract, freeze address, smoke-test deployed version | P2 | Day 6 | Urgent | to do | Day 6 - Demo Readiness
Final visual pass + mobile viewport check | P3 | Day 6 | High | to do | Day 6 - Demo Readiness
Pitch deck final; assign pitch speaking parts; README + repo cleanup for submission | P4 | Day 6 | High | to do | Day 6 - Demo Readiness
Submit EARLY (portals crash at deadline); fix only what broke in rehearsal; NO new features; rest before pitch | All | Day 7 | Urgent | to do | Day 7 - Buffer + Submit | Day 7 is buffer, not extra scope.